## Sheet1
	Sheet 7: Technical Issues Log + AI SEO Issues

Issue Type	Affected URLs Count	Severity Level	Description	Date Discovered	Status	Assigned To	Fix Implemented Date	Verification Date	AI SEO Impact Level	Answer Engine Affected	SGE Visibility Impact	Notes
Missing Alt Text	6	Medium	Product images missing alt text affecting AI image understanding	2025-06-15	In Progress	Dev Team	2025-06-18	Pending	Medium	Perplexity, ChatGPT	Low	Priority on tutorial pages
Slow Loading Pages	3	High	Pages over 3s load time affecting AI crawler efficiency	2025-06-14	Fixed	Dev Team	2025-06-17	2025-06-18	High	All Engines	Medium	Image optimization implemented
E-E-A-T Signals Missing	4	High	Author bios and expertise signals missing for AI evaluation	2025-06-13	In Progress	Content Team	2025-06-19	Pending	High	Claude, ChatGPT	High	Adding author expertise sections
Semantic Markup Incomplete	8	Medium	Missing entity markup affecting AI content understanding	2025-06-12	Open	SEO Team	Pending	Pending	High	All Engines	High	Schema.org entities needed
FAQ Schema Missing	5	Medium	No FAQ schema affecting answer engine optimization	2025-06-11	Fixed	Dev Team	2025-06-16	2025-06-17	Medium	Perplexity, SGE	Medium	Implemented on key pages
AI Content Detection	2	Low	Some pages flagged as potential AI content	2025-06-20	Open	Content Team	Pending	Pending	Medium	Google SGE	Medium	Review and enhance human elements
Long-tail Keywords Missing	7	Medium	Insufficient conversational query optimization	2025-06-18	In Progress	SEO Team	Pending	Pending	High	Voice Search, AI	High	Focus on question-based queries
Entity Relationships Weak	3	Low	Poor entity graph connections affecting topic authority	2025-06-17	Open	Content Team	Pending	Pending	Medium	Knowledge Graph	Medium	Internal linking improvements needed
Mobile Touch Elements	1	Low	Touch elements too small on mobile affecting mobile AI crawlers	2025-06-16	Fixed	UX Team	2025-06-19	2025-06-20	Low	Mobile AI	Low	Button sizing corrected
Answer Format Optimization	6	Medium	Content not optimized for direct answer extraction	2025-06-15	In Progress	Content Team	Pending	Pending	High	All Answer Engines	High	Restructuring for featured snippets